# COMIS User Acceptance Testing (UAT) Plan – 23 to 30 October 2026

2026-09-30 · Shane

# 1. Introduction and objectives

User Acceptance Testing (UAT) runs from Friday 23 October to Friday 30 October 2026, with no weekend work, as twelve half-day sessions over six working days. The first two sessions are a full day for the IT administrator on the systems they will manage; the other ten are for the cooperative society, Registrar Officer and Registrar Supervisor testers. The purpose is for the Office of the Registrar of Cooperatives to confirm that the Cooperative Management Information System (COMIS) supports its real registration, oversight and public-information processes before go-live. This plan tells the client exactly what will be tested, by whom, in which session, and how results will be judged.

The objectives of UAT are to:

Confirm that each COMIS feature delivered under the Jira Epics behaves as agreed in the approved user stories and acceptance criteria.

Let cooperative societies (applicants), Registrar Officers and Supervisors run complete end-to-end journeys using realistic Malawian cooperative data.

Identify defects and usability gaps, and classify them so that go-live decisions are based on evidence.

Obtain formal client sign-off, or a documented list of conditions, at the close of the week.

| Item | Detail |
| --- | --- |
| Document | COMIS UAT Plan, version 0.3 (draft for client review) |
| Project | Cooperative Management Information System (COMIS), Malawi |
| Format | Twelve half-day sessions: the IT administrator day (Sessions 1 and 2), then ten UAT sessions |
| UAT window | Friday 23 October to Friday 30 October 2026 (six working days, no weekend), 08:30 to 17:00 Central Africa Time (CAT) |
| Prepared by | MNS Project Management |
| Traceability | Every scenario belongs to a Jira Epic and its user stories, referred to here by Epic name |

# 2. Scope

UAT covers the 13 functional Jira Epics below, which together hold about 190 active user stories. The Dashboard Epic is exercised inside each journey rather than as a separate block, and the technical set-up Epic is not a user-facing feature. COMIS has four user roles: IT Administrator, Cooperative Society (the applicant), Registrar Officer and Registrar Supervisor. The IT Administrator's features are tested in Sessions 1 and 2; the other three roles run Sessions 3 to 12.

| Epic | Main users | Where it is tested |
| --- | --- | --- |
| User Management | IT Administrator, all roles at sign-in | Sessions 1 and 2; sign-in in Session 3 |
| System Parameters | IT Administrator | Session 2; effects seen in Sessions 4 to 11 |
| Common modules (navigation, notifications, announcements, quick links, CSV export) | All roles | Sessions 3 and 5 |
| Public Information and Search Portal | Registrar Officer (signed out), Cooperative Society | Session 7 (content managed in Session 1) |
| Assessment | Cooperative Society, Officer, Supervisor | Session 4 |
| CME Training | Cooperative Society, Officer | Session 5 |
| Cooperative Registration | Cooperative Society, Officer, Supervisor | Sessions 6 and 7 |
| Cooperative profile with By-Laws Amendment | Cooperative Society, Officer, Supervisor | Session 8 |
| Membership Management with leaders | Cooperative Society, Officer, Supervisor | Session 9 |
| Dissolution (COMIS ticketing system) | Cooperative Society, Officer, Supervisor | Session 10 (conditional) |
| Grievance Redress Mechanism (COMIS ticketing system) | Registrar Officer (public form, signed out), Supervisor | Session 10 (conditional) |
| Post-training | Cooperative Society, Officer, Supervisor | Session 11 |
| Cooperative Union | Cooperative Society, Officer, Supervisor | Session 11 |

Conditional scope. Dissolution and Grievance Redress run on the COMIS ticketing system. They are tested in Session 10 only if they meet the entry criteria in section 6; otherwise they move to a follow-up UAT cycle agreed with the client, and the session is used for retest and catch-up.

Out of scope for this UAT:

The National Registration Bureau (NRB) identity integration, which is not tested in this UAT.

Stories marked Discarded or deferred to Phase 2 in Jira.

Non-functional testing (load, performance, penetration testing), which MNS performs separately.

Off-system activities such as delivering CME training sessions or receiving payments at the bank.

# 3. UAT schedule

The whole UAT, including the IT administrator day, runs from Friday 23 to Friday 30 October 2026. The IT administrator is trained first, in Sessions 1 and 2 on Friday 23 October, so that accounts, content and reference data are ready. UAT then runs in ten half-day sessions from Monday 26 October, following the natural order of the COMIS business process: sign-in, assessment, CME, registration, profile and members, ticketing processes, then post-training and Union. One test cooperative is carried forward from Assessment in Session 4 to its Certificate in Session 7, so data created in one session feeds the next. The final session, on Friday 30 October, retests the week's fixes, offers a refresher if needed, and closes the UAT with defect management and client sign-off.

| Session | When (CAT) | Focus | Must attend |
| --- | --- | --- | --- |
| 1 | Fri 23 Oct, morning | IT admin: UI, the four systems, WordPress content, Keycloak users | IT Administrator |
| 2 | Fri 23 Oct, afternoon | IT admin: ticketing users, System Parameters, tester accounts | IT Administrator |
| 3 | Mon 26 Oct, morning | Orientation: the UI and the four systems; sign-in and common features | Cooperative Society, Officer, Supervisor |
| 4 | Mon 26 Oct, afternoon | Assessment | Cooperative Society, Officer, Supervisor |
| 5 | Tue 27 Oct, morning | CME training and common features | Cooperative Society, Officer |
| 6 | Tue 27 Oct, afternoon | Registration: submission and officer review | Cooperative Society, Officer |
| 7 | Wed 28 Oct, morning | Registration decision and certificate; public portal | Cooperative Society, Officer, Supervisor |
| 8 | Wed 28 Oct, afternoon | Cooperative profile and By-Laws Amendment | Cooperative Society, Officer, Supervisor |
| 9 | Thu 29 Oct, morning | Membership management and election of leaders | Cooperative Society, Officer, Supervisor |
| 10 | Thu 29 Oct, afternoon | Grievance redress and Dissolution (COMIS ticketing system) | Cooperative Society, Officer, Supervisor |
| 11 | Fri 30 Oct, morning | Post-training and Cooperative Union (two parallel tracks), end-to-end confirmation | Cooperative Society, Officer, Supervisor (two groups) |
| 12 | Fri 30 Oct, afternoon | Final retest, refresher if needed, defect management, client sign-off | Client UAT Lead, Registrar or delegate, Officer, Supervisor |

Who attends each session. Required means the role must be present for the whole session. On call means the role is reachable and joins when needed.

| Session | IT Administrator | Cooperative Society | Registrar Officer | Registrar Supervisor |
| --- | --- | --- | --- | --- |
| 1 and 2 (Fri 23 Oct) | Required | Not needed | Not needed | Not needed |
| 3 (Mon 26 Oct am) | On call | Required | Required | Required |
| 4 (Mon 26 Oct pm) | On call | Required | Required | Required |
| 5 (Tue 27 Oct am) | On call | Required | Required | On call |
| 6 (Tue 27 Oct pm) | On call | Required | Required | On call |
| 7 (Wed 28 Oct am) | On call | Required | Required (also runs the public portal signed out) | Required |
| 8 (Wed 28 Oct pm) | On call | Required | Required | Required |
| 9 (Thu 29 Oct am) | On call | Required | Required | Required |
| 10 (Thu 29 Oct pm) | On call (ticketing users) | Required (dissolution) | Required (also submits the public grievance form) | Required |
| 11 (Fri 30 Oct am) | On call | Required, two groups | Required, two groups (also checks the public Union profile) | Required, two groups |
| 12 (Fri 30 Oct pm) | On call | Required for the refresher | Required | Required |

The client UAT Lead and the Registrar or delegate attend Session 12 for the sign-off. The client UAT Lead attends every session if possible, and at least the first and last 30 minutes.

How each session runs. Morning sessions run 08:30 to 12:30 and afternoon sessions 13:30 to 17:00. The first 30 minutes of every UAT session from Session 4 onward retest the defects fixed since the previous session and confirm the scope of the session. The last 30 minutes of each afternoon session from Session 4 to Session 10 are for defect triage with the client UAT Lead and for the daily summary (executed, passed, failed, defects by severity). Session 11 runs Post-training and Cooperative Union in two parallel tracks. Session 12 is the closing session: final retest, a refresher if needed, defect management, and sign-off.

IT administrator day agenda (Sessions 1 and 2, Friday 23 October)

| Time (CAT) | Session | Topic |
| --- | --- | --- |
| 08:30 to 10:00 | 1 | The UI and the four systems: Keycloak, the public portal, the COMIS back-office and the COMIS ticketing system |
| 10:15 to 11:30 | 1 | WordPress: managing information content, publications and resources on the public portal |
| 11:30 to 12:30 | 1 | Keycloak: creating and managing users, roles, activation and password resets |
| 13:30 to 14:45 | 2 | COMIS ticketing system: user management |
| 14:45 to 16:30 | 2 | COMIS System Parameters, hands-on, and creation of the UAT tester accounts |
| 16:30 to 17:00 | 2 | Questions and confirmation that the environment is ready for UAT, with the client UAT Lead |

Key dates around the UAT window (proposed)

| Date | Milestone |
| --- | --- |
| Wed 21 Oct | UAT readiness review with the client; tester names and test data confirmed |
| Fri 23 Oct | IT administrator day (Sessions 1 and 2); UAT environment frozen; entry gate confirmed at 17:00 (section 6) |
| Mon 26 to Thu 29 Oct | UAT Sessions 3 to 10 |
| Fri 30 Oct | Session 11 (Post-training, Union, end-to-end confirmation) and Session 12 (final retest, defect management, sign-off meeting and UAT summary report) |

# 4. Roles and responsibilities

COMIS has four system roles. The client owns the test decisions; MNS supports, records and fixes. Names are to be confirmed at the 21 October readiness review.

| Role | Who | Responsibilities in UAT |
| --- | --- | --- |
| IT Administrator | [IT administrator, Office of the Registrar] | Attends Sessions 1 and 2; manages users in Keycloak and the ticketing system, publishes content in WordPress, maintains System Parameters; is on call during the other sessions for accounts and reference data |
| Cooperative Society (Applicant) | [4 to 6 cooperative representatives; two of them also cover the Union track in Session 11] | Execute front-office scenarios: self-registration, assessment, CME, registration, profile, by-laws, members, elections, post-training, union, dissolution |
| Registrar Officer | [3 to 4 officers] | Execute back-office scenarios: review, recommend, request amendments, reject, follow up post-training and dissolution, work grievances. Also run the signed-out public portal scenarios (Sessions 7, 10 and 11) in a private browser window, without logging in |
| Registrar Supervisor | [2 supervisors] | Execute approval and oversight scenarios: final decisions, dashboards, ticketing decisions |
| Client UAT Lead | [Name, Office of the Registrar] | Owns the UAT outcome, assigns testers to scenarios, chairs the daily triage, signs off |
| MNS UAT Coordinator | Shane Permalloo, Project Manager | Runs the schedule, environment and logistics, publishes daily reports, escalates blockers |
| MNS QA and support team | MNS QA engineers | Walk testers through scenarios, log defects in Jira, retest fixes |
| MNS Development team | MNS developers | Triage and fix defects, deploy fixes to the UAT environment overnight |

The public visitor is a persona, not a system role: the public portal needs no account, so Registrar Officers run the public portal scenarios signed out, in a private browser window. Each tester should be available for every session marked Required for their role and should attend Session 3, the orientation.

# 5. Test environment, access and test data

All testing takes place on a dedicated UAT instance of COMIS, separate from development and production, with code frozen from Friday 23 October so results stay repeatable. Testers work with four connected systems:

Keycloak: sign-in and user management for every COMIS user.

Public portal (WordPress): informative content, publications and resources, the online search of cooperative societies, and the basic public profile of each cooperative.

COMIS back-office: where cooperative societies (applicants) and the Registrar's Office carry out most cooperative management, from assessment to certificate, profile, members and leaders.

COMIS ticketing system: grievance redress and the dissolution process.

Access and data for the sessions:

Access: a current Chrome, Edge or Firefox browser and a stable internet connection at the client's premises. The URLs of all four systems are issued by MNS by 21 October.

Accounts: one named test account per tester and role, created by the IT administrator during the administrator day, including several applicant accounts so that each applicant holds one application.

Test data: realistic but non-production cooperatives, member lists, supporting documents (PDF and image samples within size limits) and payment receipts.

Email and notifications: a shared mailbox or mail-capture tool receives all system emails, so testers can verify content, recipients and timing without contacting real cooperatives.

Reference data: districts, sectors, designations, fees, reserved words and thresholds are loaded to production-like values before Session 3.

Test tracking: each scenario has an ID (UAT-xxx-nn). Testers record Pass, Fail or Blocked on the shared UAT tracker; each failure becomes a Jira defect linked to the story.

# 6. Entry criteria and pre-requisites

UAT for the cooperative society, Officer and Supervisor testers starts on Monday 26 October only if the following are met by the entry gate at 17:00 on Friday 23 October, the end of the IT administrator day.

The UAT environment is deployed, frozen and reachable by all testers, and a smoke test of sign-in, assessment, registration and the public portal has passed.

Every user story in scope has passed MNS internal QA and has no open Critical or High defect.

The IT administrator day (Sessions 1 and 2) has taken place, and all tester accounts, roles, reference data and sample documents are loaded and confirmed by the client UAT Lead.

The client has named its testers and confirmed their availability for the scheduled sessions.

Testers hold this plan and the scenario tables, and will attend the Session 3 orientation.

The defect log and UAT tracker are set up, with access for the client and MNS.

Story-level rule. Only stories that meet criterion 2 on 23 October are tested in this window. A story that is not ready is listed in the entry-gate report shared that day and moves to a follow-up cycle. This applies in particular to the ticketing-based Dissolution and Grievance workflows, which are conditional in Session 10.

# 7. Test scenarios by session

Each table lists the scenarios a tester runs, the role that runs them, and the result that counts as a pass. A scenario passes only when every expected result is met; any deviation is logged as a defect against the related user story. The scenarios follow the Jira Epics named in section 2, plus a few cross-cutting checks (role-based access, document access and audit trail). Public portal scenarios are run signed out by Registrar Officers, shown as "Officer (signed out)", so they need no separate role.

## Sessions 1 and 2 (Friday 23 October): IT Administrator day

Who attends: IT Administrator (must attend), MNS trainers. The client UAT Lead joins the readiness check at 16:30.

The IT administrator runs these scenarios hands-on during the training day, so the training doubles as acceptance of the administrator features. Session 1 covers ADM-01 to 04 and 12; Session 2 covers ADM-05 to 11.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-ADM-01 | IT Administrator | In Keycloak, create users and assign a role (Cooperative Society, Registrar Officer, Registrar Supervisor or IT Administrator), including officer and supervisor provisioning from the admin screen. Each user can sign in and sees only what the role allows. |
| UAT-ADM-02 | IT Administrator | Change a user's role, then deactivate and reactivate the account. Access changes accordingly; a deactivated user cannot sign in. |
| UAT-ADM-03 | IT Administrator | Trigger an account activation and a password reset for a user. The emails arrive and the links work. |
| UAT-ADM-04 | IT Administrator | In WordPress, publish an information page and upload a publication or resource. Both appear on the public portal, and unpublishing removes them. |
| UAT-ADM-05 | IT Administrator | In the COMIS ticketing system, create users for officers and supervisors with the right permissions. They can open their queues. |
| UAT-ADM-06 | IT Administrator | In COMIS System Parameters, view the list, search it and update a value. The change is saved and takes effect. |
| UAT-ADM-07 | IT Administrator | Maintain districts, sectors, designations, terms of office and auditor names. New values appear in the forms that use them. |
| UAT-ADM-08 | IT Administrator | Change the minimum number of members for a cooperative, of cooperatives for a Union, and of primaries for a secondary cooperative (financial and non-financial). Later forms enforce the new values. |
| UAT-ADM-09 | IT Administrator | Add a reserved word for cooperative names and configure the payment, amendment and system fees. Names and invoices follow the new settings. |
| UAT-ADM-10 | IT Administrator | Configure deadlines and notification periods and the list of post-trainings. Reminders and forms use them. |
| UAT-ADM-11 | IT Administrator | Configure a dashboard announcement and quick links in System References. They display on the COMIS dashboard. |
| UAT-ADM-12 | IT Administrator | Review the audit log after the steps above. User creation, role changes, deactivation and reactivation are recorded with user and time. |

## Session 3 (Monday 26 October, morning): orientation and sign-in

Who attends: Cooperative Society testers, Registrar Officers, Registrar Supervisors and the client UAT Lead (all must attend). The IT Administrator is on call for accounts. No defects are expected before the hands-on part at 11:00.

| Time (CAT) | Topic |
| --- | --- |
| 08:30 to 09:00 | Welcome, UAT objectives, ground rules, how to record results and log defects |
| 09:00 to 10:00 | The four systems: Keycloak for sign-in and users; the public portal (WordPress) for content, resources, cooperative search and public profile; the COMIS back-office for cooperative societies and the Registrar's Office; the COMIS ticketing system for grievances and dissolution |
| 10:00 to 11:00 | The COMIS UI by role: dashboards, navigation, notifications and status cards for Cooperative Society, Officer and Supervisor |
| 11:00 to 12:30 | Hands-on scenarios below |

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-USR-01 | Cooperative Society | Self-register a cooperative on the Front Office portal. Mandatory fields are validated, an activation email arrives, and the account can sign in after activation. |
| UAT-USR-02 | All roles | Sign in with valid credentials and land on the correct dashboard for the role; invalid credentials are rejected with a clear message. |
| UAT-USR-03 | All roles | Use Forgot Password. A reset email arrives, the link works once, and the new password allows sign-in. |
| UAT-USR-04 | All roles | Sign out. The session ends and the browser Back button does not reopen protected pages. |
| UAT-USR-05 | Cooperative Society | Registration event emails (activation and status events) arrive with correct recipient, subject and content. |
| UAT-XCT-01 | All roles | Open every menu the role can see, then try a page that belongs to another role. Menus match the role, and direct links to other roles' pages are refused. |
| UAT-CMN-01 | All roles | Use the dynamic navigation tabs, the More menu and history. Recently opened pages are listed and reopen correctly. |
| UAT-CMN-02 | All roles | Enter special characters in text fields on developed modules. Invalid input is rejected with a clear message. |
| UAT-CMN-05 | All roles | The dashboard announcement configured by the administrator displays. |
| UAT-CMN-06 | All roles | The quick links configured by the administrator display and open the right pages. |

## Session 4 (Monday 26 October, afternoon): Assessment

Who attends: Cooperative Society testers, Registrar Officers, Registrar Supervisors (must attend). IT Administrator on call.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-ASM-01 | Cooperative Society | Start an assessment, save it as a draft, reopen it, complete it and submit. The status changes to Submitted. |
| UAT-ASM-02 | Cooperative Society | Leave mandatory data blank or invalid in the Group Information, Membership, Contact Details, Committee and Meetings sections. Each section blocks submission with a specific message. |
| UAT-ASM-03 | Cooperative Society | Repeat for Record Keeping, Business, Capacity Building, Finance, Assets, Progress and Challenges, and Contact Person and Acknowledgement. |
| UAT-ASM-04 | Cooperative Society | Enter a cooperative name that uses a reserved word or duplicates an existing one. The name is rejected, and the correct suffix is added for the business type where configured. |
| UAT-ASM-05 | Cooperative Society | Try to create a second application with the same account. The system allows only one application. |
| UAT-ASM-06 | Registrar Officer | On submission, the officer receives the notification email. |
| UAT-ASM-07 | Officer, Supervisor | Search the application list, open assessments and view their details. Filters return the right records. |
| UAT-ASM-08 | Officer, Cooperative Society | Approve an assessment. The status updates and the applicant receives the approval email. |
| UAT-ASM-09 | Officer, Cooperative Society | Reject an assessment with a reason. The applicant is notified and sees the outcome. |
| UAT-ASM-10 | Cooperative Society | Track the status, view the submitted assessment and see the Assessment step card on the dashboard. |
| UAT-ASM-11 | Officer, Supervisor | The Assessment tab on the officer and supervisor dashboard shows correct counts and links to the applications. |
| UAT-ASM-12 | Officer, Cooperative Society | The officer takes a submitted assessment into review and requests an amendment with remarks. The applicant amends and resubmits, and the officer reviews the resubmission. Statuses follow Under Review, Amendment Required and Resubmitted. |
| UAT-ASM-13 | Cooperative Society, Officer | Editing is locked after submission and reopens only when an amendment is requested. A rejected assessment permanently blocks CME and registration; an approved one unlocks CME. |
| UAT-ASM-14 | Cooperative Society | Use the self-registration details to prefill the contact person. Membership totals calculate automatically, and telephone numbers must follow the Malawi format. |

## Session 5 (Tuesday 27 October, morning): CME training and common features

Who attends: Cooperative Society testers, Registrar Officers (must attend). Registrar Supervisors on call for the common-feature checks. IT Administrator on call.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-CME-01 | Cooperative Society | With an approved assessment, submit a CME request with the member list. Members must be 18 or over, at least 10 members are required, and the status becomes Pending Review. |
| UAT-CME-02 | Cooperative Society, Officer | The applicant sees the request read-only; back-office users see the request and its approved details. |
| UAT-CME-03 | Officer | The Registrar Officer receives an email on CME submission. |
| UAT-CME-04 | Officer | Place a CME request on hold with a reason; the status and the applicant view update. |
| UAT-CME-05 | Officer, Cooperative Society | Record training completion and approve CME. The applicant receives the approval email and an invoice is generated. |
| UAT-CME-06 | Cooperative Society, Officer | CME status shows correctly on both dashboards at each step. |
| UAT-CME-07 | Cooperative Society | Registration is allowed while CME is valid and blocked once it has lapsed. The validity period is confirmed by the client before UAT (see section 10). |
| UAT-CME-08 | Cooperative Society, Officer | View the details of an expired CME; the applicant receives the expiry email. |
| UAT-CME-09 | Officer, Cooperative Society | The officer requests an amendment to a CME request with remarks. The applicant amends and resubmits, and the officer is notified. |
| UAT-CME-10 | Officer, Cooperative Society | The officer uploads completion evidence when recording training completion. The record becomes read-only after completion. |
| UAT-CME-11 | Officer, Supervisor | The dashboard shows lapsing and lapsed CME. A cooperative whose CME has lapsed cannot progress until it is renewed. |
| UAT-CMN-03 | All roles | Trigger events in several modules. Bell and dashboard notifications show standard content, and cleared notifications do not reappear. |
| UAT-CMN-04 | Officer | Export search results to CSV. The file matches the on-screen results and filters. |
| UAT-CMN-07 | Cooperative Society | Completion emails contain the rating link in the footer. |

## Session 6 (Tuesday 27 October, afternoon): Registration, submission and officer review

Who attends: Cooperative Society testers, Registrar Officers (must attend). Registrar Supervisors on call. IT Administrator on call.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-REG-01 | Cooperative Society | Choose the registration journey from the dashboard and change the registration type. Options offered match the applicant's eligibility. |
| UAT-REG-02 | Cooperative Society | With an approved assessment and valid CME, create and submit a registration application, and view the completed form. Without them, registration is blocked. |
| UAT-REG-03 | Cooperative Society | Cooperative information is prefilled from earlier steps, and field validations reject invalid entries. |
| UAT-REG-04 | Cooperative Society | Enter the member list. Field validation applies, and member shareholding is calculated and validated. |
| UAT-REG-05 | Cooperative Society | Upload mandatory supporting documents. Wrong file types or oversized files are rejected. |
| UAT-REG-06 | Cooperative Society | Upload payment information. Missing or invalid payment details block submission. |
| UAT-REG-07 | Cooperative Society | The cooperative name is locked and checked for uniqueness during registration. |
| UAT-REG-08 | Officer | On submission, the officer is emailed. Search applications, open the form and check the Registration dashboard counts. |
| UAT-REG-09 | Officer | Review the application and recommend it for approval. The supervisor receives an approval-request email. |
| UAT-XCT-02 | Cooperative Society, Officer | Uploaded documents open only for the owning cooperative and for authorised back-office users. A link copied to another cooperative's account is refused. |

## Session 7 (Wednesday 28 October, morning): Registration decision, certificate and public portal

Who attends: Registrar Officers, Registrar Supervisors, Cooperative Society testers (must attend). The public portal scenarios are run signed out by Registrar Officers, in a private browser window. IT Administrator on call.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-REG-10 | Supervisor, Cooperative Society | Approve the registration. The Certificate of Registration is generated with the Director's signature and QR code, the by-laws QR code works, and the applicant receives the approval email. |
| UAT-REG-11 | Officer, Cooperative Society | Reject an application with a reason. The applicant is notified and sees the outcome. |
| UAT-REG-12 | Officer, Cooperative Society | Request an amendment. The applicant is emailed, amends and resubmits, and the officer is notified of the resubmission. |
| UAT-REG-13 | Cooperative Society, Officer | Complete a Fast Track Registration; the shortened workflow follows the agreed rules. |
| UAT-REG-14 | Cooperative Society, Officer | Editing is locked after submission and reopens only for an amendment; a registered cooperative cannot register again. |
| UAT-PUB-01 | Officer (signed out) | Browse the information pages on the public portal. Content published by the administrator displays correctly on desktop and mobile. |
| UAT-PUB-02 | Officer (signed out) | Open the Publications and Resources area, filter or search, and download a file. The file opens correctly. |
| UAT-PUB-03 | Officer (signed out) | Search for a cooperative by name or registration number. Matching registered cooperatives are listed; unregistered ones are not. |
| UAT-PUB-04 | Officer (signed out) | Open a cooperative's basic public profile. It shows only the agreed public details. |
| UAT-PUB-05 | Officer (signed out) | Scan the QR code on a Certificate of Registration. It opens the public profile of that cooperative. |
| UAT-PUB-06 | Officer (signed out) | A dissolved cooperative shows its status on the public profile, and no private data appears anywhere on the portal. |

## Session 8 (Wednesday 28 October, afternoon): Cooperative profile and By-Laws Amendment

Who attends: Cooperative Society testers, Registrar Officers, Registrar Supervisors (must attend). IT Administrator on call.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-PRF-01 | Cooperative Society | Open the cooperative profile from the dashboard and view its details. The informational banner displays as specified. |
| UAT-PRF-02 | Cooperative Society, Officer | Edit permitted profile details. The officer's profile update request email can be resent and arrives correctly. |
| UAT-PRF-03 | Officer, Supervisor | Search cooperative societies and view a full profile, including supporting documents from By-Laws Amendment applications. |
| UAT-PRF-04 | Cooperative Society | Create a By-Laws Amendment application using the enhanced creation workflow. |
| UAT-PRF-05 | Cooperative Society | An invoice is generated for the amendment; upload the payment receipt and submit. |
| UAT-PRF-06 | Cooperative Society, Officer | View the amendment form as applicant and as officer or supervisor; data matches what was submitted. |
| UAT-PRF-07 | Officer, Supervisor | The officer reviews and acts on the amendment; the supervisor takes the final decision. |
| UAT-PRF-08 | Officer, Supervisor | Search amendment applications; the dashboard and the Approved status card show correct counts. |
| UAT-PRF-09 | Cooperative Society, Officer | Amendment emails go to the applicant and to the officer at each step with correct content. |
| UAT-PRF-10 | Cooperative Society, Officer | View amendment history from the amendments list, from the cooperative profile, and as officer or supervisor. |
| UAT-PRF-11 | Cooperative Society | Transfer a cooperative to another applicant. The new applicant sees the cooperative and the previous one no longer does. |
| UAT-PRF-12 | Cooperative Society | Choose each amendment type. The mandatory fields change with the type, and the amendment fee of MWK 2,000 appears on the invoice. |
| UAT-PRF-13 | Officer, Supervisor | After approval, the previous by-laws record is archived and the profile shows the latest version. |
| UAT-XCT-03 | Officer, Supervisor | Open the history of an application, a cooperative and a member. Each action shows who did it and when. |

## Session 9 (Thursday 29 October, morning): Membership management and election of leaders

Who attends: Cooperative Society testers, Registrar Officers, Registrar Supervisors (must attend). IT Administrator on call.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-MEM-01 | Cooperative Society | View the member register and member details, add a member, edit a member, and search members. |
| UAT-MEM-02 | Officer, Supervisor | View and search members of any cooperative and see a member's history. |
| UAT-MEM-03 | Cooperative Society | Download the CSV template, fill it, and upload it. Valid rows are processed; invalid rows are reported with reasons. |
| UAT-MEM-04 | Cooperative Society | An email reports upload success or failure; a failed upload can be restarted. |
| UAT-MEM-05 | Cooperative Society | Run a first-time leader election, selecting members from the searchable dropdown. |
| UAT-MEM-06 | Cooperative Society | Create an optional subcommittee and submit the election; the confirmation email is received. |
| UAT-MEM-07 | Cooperative Society, Officer, Supervisor | View submitted elections in each role. |
| UAT-MEM-08 | Cooperative Society | View General Meeting and Annual General Meeting history; maintain, remove and replace committee members during a meeting. |
| UAT-MEM-09 | Cooperative Society, Officer | When an elected member becomes inactive, the system manages committee compliance as specified. |
| UAT-MEM-10 | Officer, Supervisor | The dashboard tracks AGM deadlines and election compliance; reminder emails go out at the configured times. |
| UAT-MEM-11 | Cooperative Society | Set the main contact person from the member list. A submitted election is read-only and cannot be edited. |

## Session 10 (Thursday 29 October, afternoon): Grievance redress and Dissolution (COMIS ticketing system)

Who attends: Registrar Officers and Registrar Supervisors (must attend), Cooperative Society testers (must attend for the dissolution requests). An Officer submits the grievance form signed out, in a private browser window. IT Administrator on call for ticketing users.

The session runs 13:30 to 14:00 retest of open fixes, 14:00 to 15:30 Dissolution, and 15:30 to 17:00 Grievance redress, followed by the daily triage. Both processes run on the COMIS ticketing system. They are conditional (see section 6): if the workflows are not ready at the entry gate, the session is used for retest and catch-up, and the ticketing scenarios move to a follow-up cycle agreed with the client.

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-DIS-01 | Cooperative Society | Submit a cooperative-initiated dissolution request; the request is recorded with the required member resolution. |
| UAT-DIS-02 | Officer | Initiate an officer-driven dissolution request. |
| UAT-DIS-03 | Officer, Supervisor | Dissolution requests reach the COMIS ticketing system, both roles process them, and the cooperative status updates to dissolved on approval. |
| UAT-DIS-04 | Officer, Supervisor, Cooperative Society | Reject a dissolution request with a reason. The cooperative stays active and the applicant is notified. |
| UAT-PUB-07 | Officer (signed out) | Submit a grievance on the public portal form. A reference is shown and the required fields are validated. |
| UAT-GRM-01 | Officer | The grievance appears in the COMIS ticketing system with the details entered on the public form. |
| UAT-GRM-02 | Officer, Supervisor | Both roles work a grievance through the agreed statuses to closure. |

## Session 11 (Friday 30 October, morning): Post-training and Cooperative Union

Who attends: Two parallel tracks, so the session needs both groups. Track A, Post-training: Cooperative Society testers, Registrar Officers, Registrar Supervisors. Track B, Cooperative Union: a second group of Cooperative Society testers, Registrar Officers, Registrar Supervisors. An Officer of Track B checks the public Union profile signed out. The IT Administrator is on call.

The session runs 08:30 to 09:00 retest of open fixes, 09:00 to 11:30 the two tracks in parallel, and 11:30 to 12:30 end-to-end confirmation and catch-up of blocked scenarios.

Track A: Post-training

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-PST-01 | Cooperative Society, Officer | The list of post-trainings maintained by the administrator appears in the request form. |
| UAT-PST-02 | Officer, Supervisor, Cooperative Society | Raise a post-training request from the dashboard; the applicant sees it in their list. |
| UAT-PST-03 | Cooperative Society | View the request details, submit the post-training application, and see the training history. |
| UAT-PST-04 | Officer, Supervisor | Search and view post-training requests. |
| UAT-PST-05 | Officer, Supervisor | Move a request through In Progress, On Hold, Completed and Rejected; each status change requires the expected data and is shown to the applicant. |
| UAT-PST-06 | Cooperative Society | Email notifications are sent for each post-training status change. |
| UAT-PST-07 | Cooperative Society, Officer | View the full post-training history of a cooperative in each role. |
| UAT-PST-08 | Officer | Taking a request off hold returns it to its previous status. |
| UAT-PST-09 | Officer, Cooperative Society | A Completed or Rejected request is read-only. A second request of the same type cannot be opened while one is active. |
| UAT-PST-10 | Officer, Supervisor | Download the post-training report. The file matches the on-screen data. |

Track B: Cooperative Union

| ID | Role | Scenario and expected result |
| --- | --- | --- |
| UAT-UNI-01 | Cooperative Society, Officer | Complete and decide a Cooperative Union assessment. |
| UAT-UNI-02 | Cooperative Society | Manage the list of primary cooperatives. Only active registered primaries can be selected, Unions never appear in the search, and the minimum number follows System Parameters (Financial 10, Non-Financial 2 by default). |
| UAT-UNI-03 | Cooperative Society, Officer, Supervisor | Register a Cooperative Union end to end and issue its certificate. |
| UAT-UNI-04 | Cooperative Society, Officer | Submit and process a Union By-Laws Amendment. |
| UAT-UNI-05 | Cooperative Society | Union members are managed correctly in Member Management. |
| UAT-UNI-06 | Cooperative Society, Officer (signed out) | The Union profile detail page shows its primary cooperatives correctly, on the back-office and the public portal. |

End-to-end journeys and retest

| ID | Journey | Where it runs | Expected result |
| --- | --- | --- | --- |
| UAT-E2E-01 | Self-register, Assessment, CME, Registration, Certificate, public QR verification | One cooperative carried through Sessions 3 to 7 | A new cooperative completes the full lifecycle with no manual data fixes, and the public portal shows it as registered. |
| UAT-E2E-02 | Rejection and amendment loop across Assessment and Registration | Sessions 4 and 7 | Amendment and resubmission keep data and history intact, and notifications go to the right people. |
| UAT-E2E-03 | Registered cooperative: profile update, By-Laws Amendment, member upload, election of leaders | Sessions 8 and 9 | Changes reflect in the profile, the public view and dashboards. |
| UAT-E2E-04 | Retest | Start of every session and Session 12 | Every defect fixed during the week is retested and closed or reopened before the sign-off. |

## Session 12 (Friday 30 October, afternoon): refresher, defect management and sign-off

Who attends: Client UAT Lead, Registrar or delegate, Registrar Officers and Supervisors (must attend). Cooperative Society testers for the refresher. IT Administrator on call. MNS Project Manager and QA lead present.

| Time (CAT) | Activity |
| --- | --- |
| 13:30 to 14:15 | Final retest of every defect fixed during the week, in the role that found it. Each is closed or reopened |
| 14:15 to 15:00 | Refresher, if needed: a targeted walk-through by MNS of areas that testers found difficult or could not complete. Skipped if the client UAT Lead confirms it is not required |
| 15:00 to 15:45 | Defect management: review all open defects by severity, confirm that no Critical or High defect is open, and agree an owner and target release for every open Medium and Low defect |
| 15:45 to 16:15 | MNS presents the UAT summary report: scenarios executed, passed, failed and deferred per Epic |
| 16:15 to 17:00 | Client sign-off: the UAT Lead records Accepted, Accepted with conditions or Not accepted on the sign-off form (section 9) |

# 8. Defect management

Every failed scenario becomes a Jira defect linked to its user story, with the scenario ID, steps, expected and actual result, and a screenshot. The client UAT Lead confirms the severity in the 16:00 triage; MNS then commits to a fix time.

| Severity | Meaning | Target response |
| --- | --- | --- |
| Critical | Blocks a core process or corrupts data; no workaround | Fix and retest within 24 hours |
| High | Major function fails or is wrong; a difficult workaround exists | Fix and retest within 48 hours, or before sign-off |
| Medium | Function works with minor error or an easy workaround | Fix in the agreed post-UAT release |
| Low | Cosmetic, wording or minor usability issue | Backlog, prioritised with the client |

Fixes are deployed to the UAT environment overnight and announced at the next morning's stand-up. A tester retests in the same environment and either closes the defect or reopens it with a comment. Requests that go beyond the approved user stories are logged as change requests, not defects, and handled through the project's change control.

# 9. Exit criteria and sign-off

UAT is complete when all of the following hold at the sign-off in Session 12 on Friday 30 October.

100% of scenarios have been executed, except those formally deferred at the entry gate.

At least 95% of executed scenarios have passed.

No Critical or High defect is open.

Every open Medium or Low defect is logged, has an agreed owner and target release, and has a workaround where needed.

The three end-to-end journeys (UAT-E2E-01 to 03) have passed.

MNS has issued the UAT summary report: scenarios executed, passed, failed and deferred per Epic, and the defect list by severity.

The client UAT Lead then records one of three outcomes on the sign-off form: Accepted, Accepted with conditions (listing the open items and dates), or Not accepted (with reasons and a proposed retest date).

| Name | Role | Decision | Signature and date |
| --- | --- | --- | --- |
| [Client UAT Lead] | Office of the Registrar of Cooperatives |  |  |
| [Registrar or delegate] | Office of the Registrar of Cooperatives |  |  |
| Shane Permalloo | Project Manager, MNS |  |  |

# 10. Risks, assumptions and dependencies

| Item | Type | Mitigation or action |
| --- | --- | --- |
| Testers are not available for their sessions | Risk | Client confirms names by 21 October; each session has a backup tester; MNS QA can guide new testers |
| Administrator day is postponed, so accounts and content are not ready | Risk | Fixed date of 23 October; MNS creates a minimum set of accounts as a fallback |
| About 120 scenarios in ten sessions is a full programme; some will not finish on time | Risk | Parallel tracks in Session 11, retest in the first 30 minutes of each session, and catch-up time in Sessions 11 and 12; the client UAT Lead prioritises if time runs short |
| Defects found late have little time to fix: a defect found on Thursday or Friday cannot go through a full fix cycle before sign-off | Risk | Critical and High defects found from Session 9 onward are fixed with priority; anything not retested by Session 12 is recorded as an open item with an owner and date |
| Email delivery delays affect the notification checks | Risk | Use a dedicated mailbox or mail-capture tool; record the delivery time in the tracker |
| Ticketing-based workflows (Dissolution and Grievance) are not ready by 23 October | Risk | Conditional Session 10; if not ready, the session is used for retest and catch-up, and the workflows move to a follow-up cycle agreed with the client |
| Internet or power interruptions at the client site | Risk | Testers pause and resume; lost time is recovered in Sessions 11 and 12 |
| The CME validity period is described as 6 months in one requirement and 12 months in another | Open decision | Client confirms the agreed value by 21 October; scenario UAT-CME-07 uses it |
| Code freeze holds after 23 October | Assumption | Only Critical and High fixes are deployed during the week |
| Approved user stories and acceptance criteria are the basis of acceptance | Assumption | New requests follow change control |
| UAT environment, accounts and data are ready by 23 October | Dependency | MNS delivers; the client confirms |